LIHEAP PLANNING FFY 19

Grant Contract Management

| Activity | Assigned | Time Line | Status | Completed |
| --- | --- | --- | --- | --- |
| FFY 2019 Spend Plan | Nancy/Heather | 06/01/18 |  |  |
| Notice of Funding Opportunity | Heather | 07/01/18 | Draft completed sent to DFAS for review 05/21/18. DFAS had a few questions. Sent back to DFAS 06/14/18. |  |
| Draft Response to NFO letters | Heather | 06/11/18 | Draft completed DFAS contract unit. | 06/08/18 |
| Agency LIHEAP Amendment Contract Draft | Heather/Lori | 08/01/18 |  |  |
| DED LIHEAP MOU | Heather/ Kathy | 08/01/18 |  |  |
| LIHEAP Invoices Issued for FFY 2018 25% Winter EA Admin. | Heather/Patti | 09/2018 |  |  |
| LIHEAP Invoices Issued for FFY 2018 75% EA Admin Winter ECIP Admin and Direct | Heather/Patti | 11/2018 |  |  |
| Income Range and Benefit Amounts determined. | Heather/Lori | 07/01/18 | Complete | 06/19/18 |
| Collect Exhibit C from LIHEAP Agencies | Lori | 11/15/18 |  |  |
| Memorandum for Program End Dates | Lori | 03/15/19 |  |  |
| Summer ECIP | Heather | 06/01/19 |  |  |
| LIHEAP Invoices Issued for Summer ECIP Direct and Summer Admin. | Heather/Patti | 05/01/19 |  |  |
| Supplier Agreements | Heather |  |  |  |
| Conduct Supplier Meetings | Heather/Sherri | 07/2018 |  |  |
| Update E1SD Supplier Detail Screen in EA system. | Heather/Sherri |  | Ongoing |  |

State Plan

| Activity | Assigned | Time Line | Status | Completed |
| --- | --- | --- | --- | --- |
| State Application Plan | Heather/Lori | 08/30/18 |  |  |
| Draft State Plan | Lori/Heather | 05/15/18 | Complete | 06/21/18 |
| Delegation letter | Lori/Heather | 05/15/18 | Complete | 06/21/18 |
| Time line for State Plan | Heather | 05/15/18 | Complete | 06/21/18 |
| Prepare Cover Letter for FSD and DSS | Heather | 05/15/18 | Complete | 06 /21/18 |
| Public Hearing | Heather | 06/2018 | Complete | 07/16/18 |
| Prepare Press Releases for Public Hearing | Lori/Heather | 05/15/18 | Complete | 06/21/18 |
| Update Public Flyer | Heather | 05/15/18 | Complete | 06/21/18 |
| State Plan, Delegation Letter and Public Hearing sent for FSD approval. | Heather | 07/01/18 | Complete | 06/21/18 |
| Update Web Site with Draft State plan | Lori | 07/12/18 | Complete | 06/29/18 |
| Update State Plan with Public Hearing Comments | Lori | 08/01/18 |  |  |
| Send State Plan for FSD and DSS final approval | Heather/Jeriane | 08/01/18 |  |  |
| Update Web Site with Final Approved State Plan | Lori | 10/2018 |  |  |
| Update State Plan with Revisions if made | Heather | 02/2019 |  |  |

Reporting

| Activity | Assigned | Time Line | Status | Completed |
| --- | --- | --- | --- | --- |
| Utilicare Reporting Households | Heather/Nancy | 07/15/16 | Received FFY 15 and FFY 16 Utilicare reports | 08/24/16 |
| Federal Report (Assisted HHLDs) | Heather/Lori | Estimate due 09/01/2018. Final report due 12/15/2018 | Will issue email for agency information 07/20/18 to be due 08/03/18 |  |
| FSD Budget Book – update after Federal Household Report to include FFY totals | Heather/Lori | 12/15/2018 |  |  |
| FSD Program Eligibility Report | Heather/Lori | 12/20/2018 |  |  |
| IM Quick Stats | Heather/Lori | 12/20/2018 |  |  |
| Leveraging Report | Heather |  |  |  |
| Carryover and Reallotment Report | Heather/ Nancy | 08/01/18 12/15/18 |  |  |
| Grantee Survey/Performance Measurement | Nancy/DFAS/Heather | 01/31/19 |  |  |

Policy

| Activity | Assigned | Time Line | Status | Completed |
| --- | --- | --- | --- | --- |
| Policy Manual Revisions and Updates Meeting | Heather/Lori/Steve | 08/2018 | Initial meeting 06/13/18. Set meeting for 06/18/18 for any additional items. |  |
| Update Policy Manual | Lori/Heather/Steve | 08/2018 |  |  |
| Review of Policy Manual Revisions | Heather | 09/2018 |  |  |
| Policy Manual Sections Sent to ITSD to convert to PDF and post on internet | Heather/Lori/Steve | 09/2018 |  |  |
| Complete Policy Manual Online | Lori/Heather/Steve | 09/15/18 |  |  |
| Update revisions from manager meeting and system changes | Heather/ Lori/Steve | 09/30/18 |  |  |
| Update Code of State Regulations 13CSR40.19010, 19020, 19030 | Steve/Lori/Heather | 05/01/16 | Complete Published | 05/31/17 |

Training

| Activity | Assigned | Time Line | Status | Completed |
| --- | --- | --- | --- | --- |
| LIHEAP Manager Meeting | Heather | 06/2018 | Held 06/12/18. | 06/12/18 |
| Develop Training Outline |  | Suspended |  |  |
| Review Training Region in EA system. Update training passwords. Ensure programming and training cases are accurate in the training region. | Sharon | 09/15/18 |  |  |
| LIHEAP Webinar | Heather/Lori/Steve | 09/2018 |  |  |
| Develop Trainer Guide |  | Suspended |  |  |
| Develop training tools |  | Suspended |  |  |
| MIS Training | Heather/Lori Steve | 09/2013 | Training set for 09/26/13. Need to set LIHEAP specific MIS training. |  |

Systems

| Activity | Assigned | Time Line | Status | Completed |
| --- | --- | --- | --- | --- |
| Supplier Usage |  | 08/2018 |  |  |
| Determine Usage Sample | Heather | 07/2018 |  |  |
| Run Usage Print reports | ITSD | 07/2018 |  |  |
| Generate mailing labels for usage suppliers | ITSD | 07/2018 |  |  |
| Validate reports | Heather/Sherri | 1/2019 |  |  |
| Mail Out Application |  |  |  |  |
| Review and revised LIHEAP application | Heather Lori/Steve | 07/01/2018 |  |  |
| Email CAA to confirm mail out return addresses | Heather | 07/2018 |  |  |
| Update E1CA and E1CO Screens | Lori/Steve | 07/2018 |  |  |
| Test Mail-Out report | Lori/Heather/Steve | 08/2018 |  |  |
| Test run of mail out applications | Lori/Heather/Steve | 08/2018 |  |  |
| Notify mail room | ISTD | 07/2018 |  |  |
| Sign off | Heather | 08/30/2018 |  |  |
| Applications Mailed out for elderly/disabled | ISTD/Mailroom | 09/15/18 |  |  |
| Applications Mailed out for all households | ISTD/Mailroom | 10/15/18 |  |  |
| On line PDF application | Lori/Heather/Steve | 09/14/18 |  |  |
| Update Web Site information with brochure information | Lori/Heather/Steve | 05/01/18 |  |  |
| CAA Security Access | Cathi | Ongoing |  |  |
| Update E1IR Income Range and Benefit screen | Heather | 08/15/18 |  |  |
| FFY17 EA System shut down for agencies | Lori/Steve | 07/15/18 |  |  |
| FFY18 EA System Update E1CM for season | Sharon | 08/15/18 |  |  |
| LIHEAP EA System Reports |  |  |  |  |
| Date of Death Match | Steve | Ongoing |  |  |
| Duplicate Address Report | Steve/Lori | Ongoing |  |  |
| Unverified SSN report | Steve | Ongoing |  |  |
| CARS | Steve | Ongoing |  |  |
| CARS Archiving | Lori | 05/2016 |  |  |
| Review Federal Outcome reporting and determine system changes. | Heather/Sharon | 01/31/18 | Working with systems. |  |
| Weekly review | Sharon/Lori | Ongoing |  |  |
| Develop EA Benefit increase projection report | Sharon/Heather | 05/01/18 | Complete | 04/20/18 |
| Set Meeting for EA Proposed Benefit Increase | Heather/Melissa | 05/15/18 |  |  |

Monitoring

| Activity | Assigned | Time Line | Status | Completed |
| --- | --- | --- | --- | --- |
| Corrective Action response for Urban League | Lori/Heather | 01/04/18 | DSS CAP response sent to agency 12/04/17 No response received. |  |
| NECAC Corrective Action Response | Lori/Heather | 02/2017 | NECAC sent CAP response. LIHEAP draft response completed 02/03/17. Cannot determine if this was sent. |  |
| Complete LIHEAP/IT DAEOC | Lori/Heather | 06/02/18 | DSS response to CAP sent to agency 05/02/18. Still findings that need to be addressed. |  |
| Complete LIHEAP/IT CAAGKC Corrective Action Follow-up | Heather | 05/17/18 | Complete | 04/02/18 |
| Complete LIHEAP/IT MVCAA | Lori/Heather | 04/19/18 | DSS response sent to agency. |  |
| Complete CAASTLC Corrective Action Plan response | Lori/Heather | 05/13/18 | Complete issued to agency 05/21/18. |  |
| Complete JFACA Revised Corrective Action Plan response | Lori/Heather | 04/21/18 | LIHEAP response complete and CSBG didn’t have anything. DFAS needs to add comments. |  |
| Complete CAPNEMO Revised Corrective Action Response | Heather | 09/22/17 | Sent to system security for review 09/22/17. Resent request 03/27/18. |  |
| Desk Monitoring | Lori | 09/30/18 | Currently reviewing. |  |
| Complete IT/LIHEAP CAPSTJOE | Steve/Lori | 05/11/18 | IT and LIHEAP Draft sent to CSBG and DFAS 05/21/18. |  |
| Complete IT/LIHEAP CAPNEMO | Steve/Lori | 05/24/18 | IT and LIHEAP draft sent to CSBG and IM manager 06/14/18. |  |
| Completed OCS Federal Monitoring Finding Response | Heather/Lori | 06/22/18 | Completed. Mailed to OCS 06/21/18. | 06/07/18 |
| Complete IT/LIHEAP CAASTLC | Steve/Heather | 06/22/18 | IT and LIHEAP draft complete sent for review 07/06/18. |  |
| Complete IT/LIHEAP MOCA | Steve/Lori | 07/20/18 | Monitoring scheduled 06/19/18-06/22/18. |  |
| Complete IT/LIHEAP CSI | Steve/Lori | 08/17/18 | Monitoring scheduled 07/17/18-07/2018. |  |
| Complete IT/LIHEAP WCMCAA | Steve/Lori | 09/07/18 | Monitoring scheduled 08/07/18-08/10/18. |  |
| Complete IT/LIHEAP OACAC | Steve/Lori | 09/21/18 | Monitoring scheduled 08/21/18-08/2418. |  |

Invoices/Payments

| Activity | Assigned | Time Line | Status | Completed |
| --- | --- | --- | --- | --- |
| Monthly LIHEAP Reports | Patti | Ongoing | Reports due the 15th of every month. |  |
| Refund checks | Sherri | Ongoing | As received. |  |

Other

| Activity | Assigned | Time Line | Status | Completed |
| --- | --- | --- | --- | --- |
| Committee to Keep Missourians Warm (CTKMW) Meetings | Heather | 01/17/13 02/27/13 03/14/13 10/10//13 11/21/13 01/16/14 04/17/14 05/15/14 10/16/14 04/16/15 10/22/15 07/21/16 10/27/16 07/20/17 10/19/17 01/18/18 04/19/18 | Did not attend Cancelled Attended Lori Attended Attended Lori Attended Attended Attended Lori Attended Attended Attended Lori Attended Attended Lori Attended Attended Attended Attended |  |
| St. Louis Metro Meeting (Ameren, Laclede, HDC, CASSTLC | Heather | 01/10/14 04/01/14 08/28/14 01/28/15 09/14/17 06/20/18 | Attended by Heather Will not attend. Attended |  |
| Kansas City Metro Meeting (KCP&L, Spire, CAAGKC) | Heather | 05/28/14 01/26/16 08/11/16 09/06/17 | Heather and Steve Milburn attended. Heather attended. Heather attended. |  |
| Spire: Laclede/MGE Meetings | Heather | 05/04/16 09/27/16 05/11/18 | Heather and Lori attended. |  |
| Update/Confirm CAA Executive Director and LIHEAP Manager email address | Cathi | 01/2018 | LIHEAP Managers completed 08/31/17 |  |
| LIHEAP Manager Desk Reference | Heather | Suspended |  |  |
| LIHEAP Desk Reference | Lori/Steve | Suspended | Parts completed and need to be reviewed |  |
| LIHEAP Supplier Desk Reference | Sherri | 12/2016 | Katherine completed. Sherri has reviewed. Needs to be reviewed and finalized. |  |
| LIHEAP Supplemental Schedule for CAA audit Report | DFAS | Ongoing | Review as part of audit report review |  |
| LIHEAP National Training | Heather/Lori | 4/30/18-05/04/18 | Attended Heather provided presentation concerning vendor management and facilitated 3 performance management sessions. | 05/04/18 |
| National Energy Utility Affordability Conference | Heather | 06/25/18 -06/29/18 | Will present 2 sessions on Performance Management. |  |
| Program Measurement Implementation Workgroup | Heather | Ongoing | In person meeting scheduled for July 9-11, 2018. | 07/13/18 |
| Program Integrity Webinar | Heather | 01/25/2018 | Completed | 01/25/18 |
| Performance Management Webinar | Heather | 04/12/18 | Complete | 04/12/18 |
| LIHEAP Peer-to-Peer Mentoring | Heather | Ongoing | Mentoring NC and IN new LIHEAP Managers. Also assisting NE and IA Managers. |  |